## Summary
DEVELOPMENT FEASIBILITY — 4 RUSSELL AVENUE, NORMAN PARK QLD 4170
5-Lot Land Subdivision · LDR Zone · 2,091 m² · 84m Corner Frontage · Prepared 27 April 2026
KEY METRICS — MID-CASE SCENARIO
Purchase Price (assumed) | 4250000
Gross Development Value (land GDV) | 6423600
Total Project Costs | 5504222
Net Profit (before tax) | 919378
Margin on Cost | 16.7%
Margin on GDV | 14.31%
Return on Equity (cash-on-cash) | 21.63%
Implied IRR (18-month hold) | 13.95%
SCENARIO COMPARISON
| LOW | MID | HIGH | STRETCH
Purchase Price | 3995000 | 4250000 | 4505000 | 3740000
Land Rate / m² | 2800 | 3000 | 3200 | 3424
GDV (land only) | 5854800 | 6423600 | 6905318.4 | 7250584.32
Total Costs | 5024603.0667 | 5504222 | 6015345.0197 | 6255958.8205
Net Profit | 830196.9333 | 919378 | 889973.3803 | 994625.4995
Margin on Cost | 16.52% | 16.7% | 14.8% | 15.9%
SUBJECT PROPERTY PROFILE
Address | 4 Russell Avenue, Norman Park QLD 4170
RPD / Lots | L3 RP104601 · L1-2 RP104602 · L73 RP45674 · L2 RP81287 (5 existing lot records)
Total Land Area | 2,091 m²
Frontage | 84 m — corner lot, dual street access potential
Zone | LDR — Low Density Residential (BCC City Plan 2014)
TBCO | NOT within Traditional Building Character Overlay — demolition unrestricted
Flood / Bushfire | 0/5 — All hazard categories zero (flood, bushfire, heritage, biodiversity)
Existing Dwelling | 88 m² under roof, built 1975 — demolishable, no planning constraint
QVAS Site Value | $1,600,000 (Oct 2024, VeryHigh confidence)
AVM Range | $1.50m – $2.03m · Mid $1.77m (Low confidence — anomalous large lot)
Proposed Lot Count | 5 standard lots (~418 m² each)
Min LDR Lot Size | 400 m² standard / 600 m² rear — all proposed lots compliant
NOTE: Blue cells are inputs (change to model scenarios). Black cells are formulas. All figures are indicative desktop estimates — verify with licensed surveyor, town planner and QS before commitment.

## Assumptions
ASSUMPTIONS — 4 Russell Avenue, Norman Park · 5-Lot Land Subdivision
Input | Value | Source / Note
ACQUISITION
Purchase Price (assumed) | 4250000 | Estimated from QVAS $1.6m site value + dev premium. Verify with licensed valuer.
Stamp Duty Rate (QLD dev site) | 5.25% | QLD transfer duty — general rate on $4.25m. Confirm with solicitor.
Stamp Duty ($) | 223125 | Calculated from purchase price × rate.
Legal / Due Diligence | 25000 | Solicitor, title search, property searches, contract review.
SITE
Total Land Area (m²) | 2091 | Stash Property / RPD data.
Number of Proposed Lots | 5 | LDR min 400m² — 2091 ÷ 5 = 418m² avg.
Average Lot Size (m²) | 418.2 | Formula: total area ÷ lot count.
Frontage (m) | 84 | Stash Property / title search.
LAND RATE ASSUMPTIONS ($/m²)
Land Rate — Low ($/m²) | 2800 | Norman Park avenue lots, conservative. Source: 10 Pattison Ave NP Jun-25 $1.95/m².
Land Rate — Mid ($/m²) | 3000 | Blended NP/Seven Hills/Camp Hill recent sales. See Comps sheet.
Land Rate — High ($/m²) | 3200 | Premium auction results. 48 McIlwraith NP Jun-25 $3,481/m².
Corner Lot Premium (Lot 1) | 8% | Estimated 8–15% corner premium over mid-block lots.
CONSTRUCTION / DEVELOPMENT
Demolition Cost | 40000 | 88m² dwelling — standard BNE rate. Add asbestos survey allowance.
Asbestos Survey & Removal Allowance | 15000 | 1975 construction — recommend asbestos assessment pre-exchange.
Surveying & Scheme Plan | 25000 | Licensed surveyor — lot geometry, scheme plan, survey plan.
BCC Planning / ROL Application | 35000 | Reconfiguration of Lot application, town planner, BCC fees.
Title Creation (5 lots) | 15000 | Titles QLD — 5 × new title creation.
Legal (subdivision) | 25000 | Solicitor — ROL, contract of sale drafting per lot.
Infrastructure Contributions (4 new lots) | 180000 | ~$45k/new lot × 4 (existing lot may be exempt). Confirm with BCC.
Site Services / Utilities Connection | 30000 | Urban Utilities, Energex connections for new lots. STCA.
Contingency (5% on dev costs) | 18250 | 5% contingency on development costs excl. acquisition.
FINANCE & HOLDING
Assumed Hold Period (months) | 18 | Estimated 12–18 months: DA + subdivision + settlement on 5 lots.
Finance Rate (annual) | 6.5% | Senior debt on purchase price. Confirm with lender.
Holding / Interest Cost | 414375 | Interest on purchase price over hold period.
Land Tax Allowance | 20000 | QLD land tax on site during hold. Confirm with accountant.
SALES & MARKETING
Agent Commission (% of GDV) | 2% | ~2% of GDV across 5 lot sales.
Marketing & Advertising Budget | 50000 | Photography, drone, digital, print per lot allowance.
Settlement / Conveyancing (vendor side) | 10000 | 5 × settlements, solicitor, disbursements.

## GDV
GROSS DEVELOPMENT VALUE (GDV) — 5-Lot Land Subdivision · Sell as Vacant Lots
Lot | Area (m²) | Land Rate ($/m²) | Gross Value | Premium / Adj. | Notes
Lot 1 — Corner (Russell Ave) | 418 | 3240 | 1354320 | 280000% | Corner premium applied — dual frontage to Russell Ave and side street.
Lot 2 — Mid-block (Russell Ave) | 418 | 3000 | 1254000 | 0% | Standard mid-block LDR lot fronting Russell Avenue.
Lot 3 — Mid-block (Russell Ave) | 418 | 3000 | 1254000 | 0% | Standard mid-block LDR lot fronting Russell Avenue.
Lot 4 — Mid-block (Russell Ave) | 418 | 3000 | 1254000 | 0% | Could front side street if corner geometry allows — surveyor to confirm.
Lot 5 — Corner (side street) | 419 | 3120 | 1307280 | 140000% | Rear corner — modest premium vs Lot 1 (less principal street exposure).
GROSS DEVELOPMENT VALUE SUMMARY — MID / LOW / HIGH
Metric | MID | LOW | HIGH | Stretch | Note
Total GDV — 5 lots (Mid rate) | 6423600 | 5854800 | 6905318.4 | 7226496 | Low = total area × low rate (flat). Mid/High include corner premium.
Average $/m² (blended) | 3072.023 | 2800 | 3302.4 | 3456 | Blended $/m² across all 5 lots including corner premiums.
Average Lot Value | 1284720 | 1170960 | 1381063.68 | 1445299.2 | Average sale price per lot.
LAND COMPARABLE SALES — BENCHMARK DATA (source: Stash Property)
Address | Sold | Sale Price | Land (m²) | $/m² | Notes
48 McIlwraith Ave, Norman Park | Jun-25 | 1410000 | 405 | 3481 | Avenue address, city views — closest to subject
10 Pattison Ave, Norman Park | Jun-25 | 1250000 | 642 | 1947 | Larger block — size discount applies
41 Watson St, Camp Hill | Jul-25 | 2385000 | 599 | 3981 | Auction — city views, north aspect, premium pocket
22 Hobart Ave, Camp Hill | Jul-25 | 1780000 | 607 | 2933 | Flat cleared site, 15m frontage
13 Margaret St, Camp Hill | Aug-25 | 1885000 | 607 | 3105 | Auction, 15m frontage, premium Camp Hill
16 Halland Tce, Camp Hill | Jul-25 | 1275000 | 405 | 3148 | North-to-rear, city views, St Thomas precinct
Isis Cres, Seven Hills (prepd) | Mar-26 | 1400000 | 530 | 2642 | Groundworks commenced, plans approved
Adopted blended rate (mid — NP/7Hills) |  | 84

## Costs
PROJECT COSTS — 4 Russell Avenue, Norman Park · Mid / Low / High Scenarios
Cost Item | MID | LOW | HIGH | Note
ACQUISITION COSTS
Purchase Price | 4250000 | 3995000 | 4505000 | Assumed market value — no public sale history
Stamp Duty | 223125 | 209737.5 | 236512.5 | QLD transfer duty on purchase price
Legal / DD | 25000 | 22500 | 28750 | Solicitor, title search, due diligence
ACQUISITION COSTS — SUBTOTAL | 4498125 | 4227237.5 | 4770262.5
DEMOLITION & SITE
Demolition | 40000 | 34000 | 50000 | 88m² dwelling removal
Asbestos Survey & Remove | 15000 | 12000 | 22500 | 1975 build — asbestos survey mandatory pre-demo
DEMOLITION & SITE — SUBTOTAL | 55000 | 46000 | 72500
PLANNING & LEGAL
Surveying & Scheme Plan | 25000 | 22500 | 30000 | Licensed surveyor — lot geometry and survey plan
BCC Planning / ROL | 35000 | 29750 | 43750 | ROL application, town planner, BCC fees
Title Creation (5 lots) | 15000 | 13500 | 16500 | Titles QLD — 5 new title creations
Legal (subdivision) | 25000 | 22500 | 28750 | Solicitor — ROL, vendor contracts x5
PLANNING & LEGAL — SUBTOTAL | 100000 | 88250 | 119000
INFRASTRUCTURE
Infra Contributions (BCC/UU) | 180000 | 153000 | 207000 | ~$45k per new lot × 4 new lots. Confirm with BCC.
Site Services / Utilities | 30000 | 24000 | 39000 | Energex, Urban Utilities connections — indicative
INFRASTRUCTURE — SUBTOTAL | 210000 | 177000 | 246000
CONTINGENCY
Development Cost Contingency | 18250 | 12775 | 23725 | 5% on dev costs. Low: 3.5%, High: 6.5%
CONTINGENCY — SUBTOTAL | 18250 | 12775 | 23725
FINANCE & HOLDING
Interest / Holding Cost | 414375 | 302954.1667 | 536845.8333 | 18-month hold mid, 14 low, 22 high
Land Tax Allowance | 20000 | 16000 | 26000 | QLD land tax during hold — confirm with accountant
FINANCE & HOLDING — SUBTOTAL | 434375 | 318954.1667 | 562845.8333
SALES & MARKETING
Agent Commission | 128472 | 105386.4 | 145011.6864 | ~2% of GDV
Marketing & Advertising | 50000 | 40000 | 65000 | Professional photography, digital, print × 5 lots
Conveyancing (vendor) | 10000 | 9000 | 11000 | 5 × settlements, solicitor disbursements
SALES & MARKETING — SUBTOTAL | 188472 | 154386.4 | 221011.6864
TOTAL PROJECT COSTS (excl. tax) | 5504222 | 5024603.0667 | 6015345.0197

## Sensitivity
SENSITIVITY ANALYSIS — Net Profit ($) by Purchase Price × Land Rate ($/m²)
Purchase Price ↓ / Land Rate → | 2400 | 2600 | 2800 | 3000 | 3200 | 3400 | 3600
3750000 | -100595482.44 | -100177449.72 | -99759417 | -836712784375.1 | -836712083375.1 | -836711382375.1 | -836710681375.1
4000000 | -107608607.44 | -107190574.72 | -106772542 | -892494284375.1 | -892493583375.1 | -892492882375.1 | -892492181375.1
4250000 | -114621732.44 | -114203699.72 | -113785667 | -948275784375.1 | -948275083375.1 | -948274382375.1 | -948273681375.1
4500000 | -121634857.44 | -121216824.72 | -120798792 | -1.0041e+12 | -1.0041e+12 | -1.0041e+12 | -1.0041e+12
4750000 | -128647982.44 | -128229949.72 | -127811917 | -1.0598e+12 | -1.0598e+12 | -1.0598e+12 | -1.0598e+12
5000000 | -135661107.44 | -135243074.72 | -134825042 | -1.1156e+12 | -1.1156e+12 | -1.1156e+12 | -1.1156e+12
NOTE: Assumes mid-case development costs, 18-month hold, 6.5% finance rate, 5.25% stamp duty. Change Assumptions sheet inputs to model alternative scenarios. Positive = profitable; negative = loss.
SENSITIVITY — Margin on Cost (%) by Purchase Price × Land Rate ($/m²)
Purchase Price ↓ / Land Rate → | 2400 | 2600 | 2800 | 3000 | 3200 | 3400 | 3600
3750000 | -0.01202% | -0.01197% | -0.01192% | -100% | -100% | -100% | -100%
4000000 | -0.01206% | -0.01201% | -0.01196% | -100% | -100% | -100% | -100%
4250000 | -0.01209% | -0.01204% | -0.012% | -100% | -100% | -100% | -100%
4500000 | -0.01211% | -0.01207% | -0.01203% | -100% | -100% | -100% | -100%
4750000 | -0.01214% | -0.0121% | -0.01206% | -100% | -100% | -100% | -100%
5000000 | -0.01216% | -0.01212% | -0.01209% | -100% | -100% | -100% | -100%

## Lot Schedule
LOT SCHEDULE & SETTLEMENT TRACKER — 4 Russell Avenue, Norman Park
Lot # | Description | Area (m²) | Land Rate ($/m²) | List Price | Sale Price | Settled? | Notes
1 | Corner — Russell Ave / side street | 418 | 235284 | 98348712 |  | No | Corner premium. Dual frontage. Stash link: TBC after title creation.
2 | Mid-block — Russell Ave | 418 | 84 | 35112 |  | No | Standard LDR lot. Mid-block position.
3 | Mid-block — Russell Ave | 418 | 84 | 35112 |  | No | Standard LDR lot. Mid-block position.
4 | Mid-block — Russell Ave / side | 418 | 84 | 35112 |  | No | Could front side street — surveyor to confirm.
5 | Rear corner — side street | 419 | 117684 | 49309596 |  | No | Rear corner. Modest premium vs Lot 1.
|  | 2091 |  | 147763644 | 0
PROJECT MILESTONES & TIMELINE
# | Milestone | Target Date | Responsible | Status |  |  | Notes
1 | Title search — confirm 5 RPD status | Week 1 | Solicitor | Pending
2 | Pre-application meeting with BCC | Week 2 | Town Planner | Pending
3 | Independent certified valuation | Week 2 | API Valuer | Pending
4 | Surveyor engaged — scheme plan | Week 3 | Lic. Surveyor | Pending
5 | Exchange of contracts | TBC | Solicitor | Pending
6 | Settlement | TBC | Solicitor | Pending
7 | Asbestos assessment | Post-settlement | Asbestos Assessor | Pending
8 | Demolition of existing dwelling | Post-settlement | Demolition Co. | Pending
9 | ROL / reconfiguration lodgement | Month 2–3 | Town Planner | Pending
10 | BCC approval of ROL | Month 4–6 | BCC | Pending
11 | Survey plan sealed | Month 6–7 | Lic. Surveyor | Pending
12 | New titles issued | Month 7–8 | Titles QLD | Pending
13 | Marketing launch — 5 lots | Month 8 | Agent | Pending
14 | All lots settled | Month 12–18 | Solicitor | Pending